## Read Me
Accountant panel - test cases
Scope | Only the accountant panel: login and menu, dashboard, invoice upload, review and submit, row validation, invoice list and details, the five invoice statuses, outstanding, record payment, payment list, TDS, tasks, layout and responsive checks, security, database checks and end-to-end scenarios. Admin, supervisor, technician and client panels are not included.
Reflects the current app | Upload only checks the file; nothing is saved until you click Submit on Review & Validate. A 'Successfully uploaded' pop-up appears after upload. Overdue is stored in the database as well as shown on screen. The menu item is TDS. The payment field is UTR No. Add Previous TDS enables only when a fully paid invoice still has TDS pending.
How to use | 1) Filter 'Test Cases' by Module, Type or Priority. 2) Follow the steps with the data named in 'Test Data'. 3) Compare with 'Expected Result', write what you saw in 'Actual Result' and choose a Status. 4) Put failures in 'Defect Log'. 5) 'Summary' updates by itself.
Status values | Not Run (default), Pass, Fail, Blocked, Skipped. Pass % = Pass / (Pass + Fail + Blocked).
Priority | P1 Critical (money, TDS, statuses, security, data loss) · P2 High · P3 Medium · P4 Low.
Basis column | Code = the behaviour was read from the repository and checked. Design = the agreed TDS design. Standard = good practice; the exact behaviour is not fixed in code, so record what you see.
Test data | All customers, sites and invoices are made up. The upload files are in docs/test-data/upload-pack/. The customers and sites exist in the test database (see 'Test Data'). Nothing was taken from real data.
Run order | 1) Set up the test customers (already done in the database). 2) Upload and Submit ALL_CASES_invoice_upload_TDS2pct.xlsx. 3) Run the payments from its 'Payments to Record' sheet. 4) Then the validation, edge, five-status and file-level files. Submit ALL_CASES before VALIDATION, because one validation row repeats an invoice number from it.
Known gaps to decide | • The accountant panel has no Cancel button for an invoice. • Payment List shows cash only, not TDS. • The TDS page accepts any rate from 0 to 100 (only 2% is meant to be used). • Payment Tracking and Customer Outstanding are not in the menu (URL only). • A remark longer than 1000 characters or an amount with more than 2 decimals is accepted by the review but may behave oddly on Submit (see the EDGE file).

## Summary
Execution summary (updates from the Test Cases sheet)
Module | Total | Pass | Fail | Blocked | Skipped | Not Run | Progress % | Pass %
Login, Menu & Access | 16 | 0 | 0 | 0 | 0 | 16 | 0% | 0%
Dashboard | 24 | 0 | 0 | 0 | 0 | 24 | 0% | 0%
Invoice Upload | 25 | 0 | 0 | 0 | 0 | 25 | 0% | 0%
Review & Validate and Submit | 23 | 0 | 0 | 0 | 0 | 23 | 0% | 0%
Row Validation (per row of the upload) | 47 | 0 | 0 | 0 | 0 | 47 | 0% | 0%
Invoice List & Invoice Details | 20 | 0 | 0 | 0 | 0 | 20 | 0% | 0%
Invoice Status (five statuses) | 21 | 0 | 0 | 0 | 0 | 21 | 0% | 0%
Outstanding, Customer Outstanding & Payment Tracking | 13 | 0 | 0 | 0 | 0 | 13 | 0% | 0%
Record Payment | 42 | 0 | 0 | 0 | 0 | 42 | 0% | 0%
Payment List | 10 | 0 | 0 | 0 | 0 | 10 | 0% | 0%
TDS | 19 | 0 | 0 | 0 | 0 | 19 | 0% | 0%
Tasks & Reminders | 11 | 0 | 0 | 0 | 0 | 11 | 0% | 0%
Layout, Responsive & Usability | 59 | 0 | 0 | 0 | 0 | 59 | 0% | 0%
Security | 8 | 0 | 0 | 0 | 0 | 8 | 0% | 0%
Database Checks (phpMyAdmin / SQL) | 11 | 0 | 0 | 0 | 0 | 11 | 0% | 0%
End-to-End Scenarios | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
TOTAL | 355 | 0 | 0 | 0 | 0 | 355 | 0% | 0%
By priority | Total | Pass | Fail | Blocked | Skipped | Not Run
P1 | 158 | 0 | 0 | 0 | 0 | 158
P2 | 121 | 0 | 0 | 0 | 0 | 121
P3 | 51 | 0 | 0 | 0 | 0 | 51
P4 | 25 | 0 | 0 | 0 | 0 | 25
By type | Total
Boundary | 10
Compatibility | 1
Design | 6
Functional | 132
Integration | 25
Negative | 25
Performance | 1
Responsive | 52
Security | 19
UI/UX | 32
Usability | 2
Validation | 50

## Test Cases
Test ID | Module | Screen / Area | Scenario | Type | Priority | Pre-condition | Test Steps | Test Data | Expected Result | Basis | Actual Result | Status | Tester | Executed On | Defect ID / Remarks
ACC-001 | Login, Menu & Access | Login | Accountant logs in | Functional | P1 | Accountant user is active | 1. Open /login 2. Tick Terms 3. Enter the accountant email and password 4. Click Login | Accountant user | Lands on /accountant (dashboard); header shows 'Accountant Panel', bell icon and user icon | Code |  | Not Run
ACC-002 | Login, Menu & Access | Login | Wrong password | Negative | P1 | - | 1. Enter the accountant email with a wrong password | Wrong@999 | Alert 'Invalid credentials'; stays on /login | Code |  | Not Run
ACC-003 | Login, Menu & Access | Login | Login button disabled until Terms is ticked | Validation | P2 | - | 1. Fill email and password 2. Leave Terms unticked | - | Login button stays disabled | Code |  | Not Run
ACC-004 | Login, Menu & Access | Session | Refresh keeps the user logged in | Functional | P2 | Logged in | 1. Press F5 on Invoice List | - | Same page reloads; still logged in | Standard |  | Not Run
ACC-005 | Login, Menu & Access | Session | Logout | Functional | P1 | Logged in | 1. User icon > Logout 2. Press Back | - | Returns to /login; Back does not show a protected page | Standard |  | Not Run
ACC-006 | Login, Menu & Access | Session | Invalid or expired token | Security | P1 | Logged in | 1. Change the token in localStorage to random text 2. Click any menu item | - | Redirected to /login | Code |  | Not Run
ACC-007 | Login, Menu & Access | Menu | Sidebar items and order | UI/UX | P2 | Logged in | 1. Look at the sidebar | - | Dashboard; Invoices (Invoice Upload, Review & Validate, Invoice List, Outstanding); Payments (Record Payment, Payment List); Tasks & Reminders; TDS | Code |  | Not Run
ACC-008 | Login, Menu & Access | Menu | Every menu item opens the right page | Functional | P1 | Logged in | 1. Click each menu item in turn | - | Each opens its own page with a matching heading; the active item is highlighted | Code |  | Not Run
ACC-009 | Login, Menu & Access | Menu | Invoices and Payments groups expand and collapse | UI/UX | P3 | - | 1. Click Invoices and Payments | - | Sub-menus open and close | Code |  | Not Run
ACC-010 | Login, Menu & Access | Menu | Payment Tracking and Customer Outstanding are not in the menu | Functional | P3 | - | 1. Open /accountant/invoices/tracking and /accountant/payments/customer-outstanding by URL | - | Both pages open and work (they are reachable by URL only) | Code |  | Not Run
ACC-011 | Login, Menu & Access | Access | Other roles cannot open /accountant | Security | P1 | Logged in as admin, supervisor, technician and client in turn | 1. Type /accountant in the address bar | Each role | Redirected to that role's own home; accountant pages never shown | Code |  | Not Run
ACC-012 | Login, Menu & Access | Access | Not logged in | Security | P1 | Logged out | 1. Open /accountant/invoices/list | - | Redirected to /login | Code |  | Not Run
ACC-013 | Login, Menu & Access | Access | Accountant cannot open admin pages | Security | P1 | Logged in as accountant | 1. Open /admin and /supervisor | - | Redirected back to /accountant | Code |  | Not Run
ACC-014 | Login, Menu & Access | Access | Only own-branch data is visible | Security | P1 | Customers with sites in two branches (Head Office and abc) | 1. Open Invoice List, Payment List, TDS page | SFC10 and BCI22 sites are in branch abc | Invoices and customers of the other branch (abc) never appear | Code |  | Not Run
ACC-015 | Login, Menu & Access | Header | Bell icon shows the unread count and opens the list | Functional | P2 | Unread notifications exist | 1. Look at the bell 2. Click it | - | Icon with a count badge (99+ when over 99); list opens; clicking an item opens its page | Code |  | Not Run
ACC-016 | Login, Menu & Access | Profile | Change own password | Functional | P2 | Logged in | 1. User icon > Profile > Change password 2. Current + new password (6+ characters) 3. Save 4. Log in with the new password | - | Password changed; old one no longer works; wrong current password gives 'Current password is incorrect' | Code |  | Not Run
DSH-001 | Dashboard | Dashboard | Default date range | Functional | P1 | - | 1. Open Dashboard | - | From = 1st of the current month, To = today; numbers cover only that range | Code |  | Not Run
DSH-002 | Dashboard | Dashboard | Six tiles show the right numbers | Functional | P1 | Invoices from the ALL_CASES file submitted | 1. Clear both dates 2. Compare the tiles with the Invoice List | See Test Data sheet | Total Invoices, Total Collected, Outstanding, Overdue, Due This Week and Today's Follow-ups match the list | Code |  | Not Run
DSH-003 | Dashboard | Dashboard | Total Invoices excludes cancelled invoices | Functional | P2 | One invoice cancelled | 1. Compare the tile with the list | - | Cancelled invoice is not counted | Code |  | Not Run
DSH-004 | Dashboard | Dashboard | Total Collected uses cash + TDS settled on invoices | Functional | P2 | Payment with TDS recorded | 1. Record cash 49,000 + TDS 1,000 on a 50,000 invoice 2. Open Dashboard | - | Total Collected grows by 50,000 (the TDS counts as settled) | Code |  | Not Run
DSH-005 | Dashboard | Dashboard | Overdue tile uses the Overdue status | Functional | P1 | Invoices past their due date | 1. Compare the Overdue tile with the Overdue tab | - | Amount and count equal the sum of pending on Overdue invoices | Code |  | Not Run
DSH-006 | Dashboard | Dashboard | Due This Week counts today up to +7 days | Boundary | P2 | Invoices due today, +7 and +8 days | 1. Read the Due This Week tile | ALL_CASES cases 12, 15, 16 | Due today and in exactly 7 days are counted; +8 days is not | Code |  | Not Run
DSH-007 | Dashboard | Dashboard | Type a From and To date | Functional | P1 | - | 1. Click From, type 01092026 2. Click To, type 30092026 | 01/09/2026 - 30/09/2026 | Slashes added (dd/mm/yyyy); all tiles, charts and lists update | Code |  | Not Run
DSH-008 | Dashboard | Dashboard | Pick a date from the calendar icon | Functional | P1 | - | 1. Click the calendar icon 2. Choose a date | - | Chosen date is visible in the box; data updates | Code |  | Not Run
DSH-009 | Dashboard | Dashboard | Half-typed date | UI/UX | P3 | - | 1. Type 0109 in From 2. Click elsewhere | 0109 | '01/09' stays visible with an amber border; not used as a filter | Code |  | Not Run
DSH-010 | Dashboard | Dashboard | Clear both dates | Functional | P2 | - | 1. Delete From and To | - | All-time numbers shown | Code |  | Not Run
DSH-011 | Dashboard | Dashboard | Invoices counted by invoice date | Functional | P1 | Invoices dated in different months | 1. Set From and To around one month | - | Only invoices whose Invoice Date is in the range are counted | Code |  | Not Run
DSH-012 | Dashboard | Dashboard | Filters and Reset | Functional | P2 | - | 1. Open Filters 2. Choose customer, site, status, mode 3. Reset | - | Reset clears the choices and returns the dates to this month; disabled when nothing to reset | Code |  | Not Run
DSH-013 | Dashboard | Trend chart | Invoiced bars use the invoice date | Functional | P1 | Invoices dated April to September 2026 | 1. Clear the dates 2. Hover each month on the Invoice & Collection Trend | - | Invoiced = sum of invoice amounts dated in that month; only the last 6 months are shown | Code |  | Not Run
DSH-014 | Dashboard | Trend chart | Collected bars use the payment date | Functional | P1 | Payments in different months | 1. Hover the months | - | Collected = cash received on payments dated in that month | Code |  | Not Run
DSH-015 | Dashboard | Trend chart | Invoiced is 0 when no invoice is dated in that month | Functional | P2 | Only invoices dated 2019-2025 | 1. Hover July 2026 | - | Invoiced ₹0 (older invoices are outside the 6 months) | Code |  | Not Run
DSH-016 | Dashboard | Trend chart | Invoice dated later than the To date | Boundary | P3 | Invoice dated 30/09/2026, today 21/09/2026 | 1. Leave the default range | - | That invoice is not counted until the date range includes it | Code |  | Not Run
DSH-017 | Dashboard | Payment Status | Donut counts by displayed status | Functional | P2 | Invoices in all statuses | 1. Read Paid / Partial / Pending / Overdue counts | - | Counts and percentages add up to the invoices in range; cancelled excluded | Code |  | Not Run
DSH-018 | Dashboard | Tables | Top Outstanding Customers | Functional | P3 | - | 1. Read the table 2. Click View All | - | Sorted by outstanding, largest first; View All opens the list | Code |  | Not Run
DSH-019 | Dashboard | Tables | Recent Payments | Functional | P3 | Payments exist | 1. Read the table 2. Click View All | - | Latest payments shown; View All opens Payment List | Code |  | Not Run
DSH-020 | Dashboard | Tables | Upcoming Reminders & Tasks | Functional | P3 | Open tasks exist | 1. Read the table | - | Open tasks in date order; 'No upcoming reminders' when none | Code |  | Not Run
DSH-021 | Dashboard | Follow-ups | Today's Follow-ups tile | Functional | P3 | A task due today | 1. Add a reminder due today 2. Open Dashboard | - | Tile shows the number of open tasks due today | Code |  | Not Run
DSH-022 | Dashboard | Loading | Skeleton while loading, empty states after | UI/UX | P3 | Slow network | 1. Open Dashboard with throttled network | - | Pulsing placeholders, then data or 'No ... yet' messages; no stuck skeleton | Code |  | Not Run
DSH-023 | Dashboard | Errors | Backend down | Negative | P2 | Backend stopped | 1. Open Dashboard | - | Error message with a Try again link; works after the backend is back | Code |  | Not Run
DSH-024 | Dashboard | Layout | Greeting and header | UI/UX | P4 | - | 1. Open Dashboard | - | 'Good Morning/Afternoon/Evening, <name>' | Code |  | Not Run
UPL-001 | Invoice Upload | Screen | Page content | UI/UX | P2 | - | 1. Open Invoice Upload | - | Title 'Upload Invoices', drop area, Select Excel File, info note, Upload & Validate (disabled), Recent Uploads, Download Template | Code |  | Not Run
UPL-002 | Invoice Upload | Template | Download the template | Functional | P2 | - | 1. Click Download Template | - | File with headers Invoice No, Customer, Site, Invoice Date, Due Date, Amount, Remarks | Code |  | Not Run
UPL-003 | Invoice Upload | File | Choose a valid .xlsx | Functional | P1 | - | 1. Click Select Excel File 2. Pick ALL_CASES_invoice_upload_TDS2pct.xlsx | ALL_CASES_invoice_upload_TDS2pct.xlsx | File name chip appears; Upload & Validate becomes enabled | Code |  | Not Run
UPL-004 | Invoice Upload | File | Drag and drop | UI/UX | P3 | - | 1. Drag the file onto the drop area | ALL_CASES_invoice_upload_TDS2pct.xlsx | Same as choosing it | Code |  | Not Run
UPL-005 | Invoice Upload | File | Remove the chosen file | Functional | P4 | File chosen | 1. Click the X on the file chip | - | Chip removed; button disabled again | Code |  | Not Run
UPL-006 | Invoice Upload | File | Upload button disabled with no file | Validation | P2 | - | 1. Open the page | - | Upload & Validate is disabled | Code |  | Not Run
UPL-007 | Invoice Upload | File | Wrong file type (PDF, image) | Negative | P1 | - | 1. Choose file_level_checks/04_wrong_type.pdf, then 05_wrong_type.png | 04_wrong_type.pdf, 05_wrong_type.png | Rejected with a clear message; nothing uploaded | Code |  | Not Run
UPL-008 | Invoice Upload | File | File over 5 MB | Boundary | P2 | - | 1. Choose file_level_checks/06_over_5MB.xlsx | 06_over_5MB.xlsx (5.6 MB) | 'The file is too large (maximum 5 MB)' | Code |  | Not Run
UPL-009 | Invoice Upload | File | Missing required columns | Negative | P1 | - | 1. Upload file_level_checks/01_missing_columns.xlsx | 01_missing_columns.xlsx | 'The file is missing these columns: Site, Amount. Please use the template.' | Code |  | Not Run
UPL-010 | Invoice Upload | File | Headers only | Negative | P2 | - | 1. Upload file_level_checks/02_headers_only.xlsx | 02_headers_only.xlsx | 'The file has no invoice rows.' | Code |  | Not Run
UPL-011 | Invoice Upload | File | Corrupt file named .xlsx | Negative | P2 | - | 1. Upload file_level_checks/03_corrupt_file.xlsx | 03_corrupt_file.xlsx | 'The file could not be read. Please upload a valid .xlsx or .csv file.' | Code |  | Not Run
UPL-012 | Invoice Upload | File | 5000 rows accepted, 5001 rejected | Boundary | P2 | - | 1. Upload 07_5000_rows.xlsx 2. Upload 08_5001_rows.xlsx | file_level_checks/07 and 08 | 5000: accepted (5000 valid); 5001: 'The file has more than 5000 rows. Please split it into smaller files.' | Code |  | Not Run
UPL-013 | Invoice Upload | File | Alternate header names and column order | Functional | P2 | - | 1. Upload file_level_checks/09_alternate_headers.xlsx | 09_alternate_headers.xlsx | 8 rows valid; extra column ignored | Code |  | Not Run
UPL-014 | Invoice Upload | Upload | Upload & Validate saves nothing yet | Functional | P1 | Empty invoices table | 1. Upload ALL_CASES_invoice_upload_TDS2pct.xlsx 2. Look at Invoice List and the database | ALL_CASES_invoice_upload_TDS2pct.xlsx | Invoice List stays empty; database has 1 invoice_imports row (PREVIEWED) and 42 invoice_import_rows; invoices table has 0 rows | Code |  | Not Run
UPL-015 | Invoice Upload | Upload | Success pop-up appears | UI/UX | P1 | - | 1. Upload a valid file | ALL_CASES_invoice_upload_TDS2pct.xlsx | 'Successfully uploaded' pop-up top-right with file name and counts; opens Review & Validate | Code |  | Not Run
UPL-016 | Invoice Upload | Upload | Pop-up closes by itself and does not return on refresh | UI/UX | P3 | - | 1. Wait about 7 seconds 2. Refresh the page | - | Pop-up disappears; not shown again after refresh; X closes it earlier | Code |  | Not Run
UPL-017 | Invoice Upload | Upload | Pop-up when nothing is valid | UI/UX | P3 | A file where every row is wrong | 1. Upload it | - | Amber pop-up 'Uploaded, but nothing can be imported' | Code |  | Not Run
UPL-018 | Invoice Upload | Upload | Busy state | UI/UX | P4 | - | 1. Click Upload & Validate on a large file | 07_5000_rows.xlsx | Button shows 'Checking file…' and is disabled meanwhile | Code |  | Not Run
UPL-019 | Invoice Upload | Upload | Network problem | Negative | P3 | Backend stopped | 1. Click Upload & Validate | - | 'Network problem. Please check your connection and try again.'; can retry | Code |  | Not Run
UPL-020 | Invoice Upload | Recent uploads | List of past uploads | Functional | P3 | Uploads exist | 1. Look at Recent Uploads | - | File names listed; 'No uploads yet' when empty; clicking one opens its Review | Code |  | Not Run
UPL-021 | Invoice Upload | Recent uploads | Remove an upload that was not submitted | Functional | P2 | A previewed upload | 1. Click X on it 2. Confirm | - | Confirm text says records will be discarded; upload and its rows deleted from the database | Code |  | Not Run
UPL-022 | Invoice Upload | Recent uploads | Remove an upload that was submitted | Functional | P2 | A submitted upload | 1. Click X on it 2. Confirm | - | Confirm text says invoices stay; the invoices remain; invoice_imports and invoice_import_rows rows are deleted | Code |  | Not Run
UPL-023 | Invoice Upload | Recent uploads | Cancel the confirmation | Functional | P4 | - | 1. Click X then Cancel in the pop-up | - | Nothing removed | Code |  | Not Run
UPL-024 | Invoice Upload | Info note | Note explains the Submit step | UI/UX | P4 | - | 1. Read the blue note | - | Says the file is checked first and nothing is saved until Submit | Code |  | Not Run
UPL-025 | Invoice Upload | Upload | Same file twice | Negative | P2 | File already submitted | 1. Upload it again 2. Open Review | ALL_CASES_invoice_upload_TDS2pct.xlsx | Every row is an error: 'Duplicate invoice number: this customer already has this invoice'; Submit disabled | Code |  | Not Run
REV-001 | Review & Validate and Submit | Review | Counts and tabs | Functional | P1 | A mixed file uploaded | 1. Open Review & Validate | VALIDATION_all_cases_invoice_upload.xlsx | Total Records, Valid, Errors tiles; tabs All (n), Valid (n), Errors (n) with the same counts | Code |  | Not Run
REV-002 | Review & Validate and Submit | Review | Row numbers equal Excel row numbers | Functional | P2 | - | 1. Compare with the Excel file | VALIDATION_all_cases_invoice_upload.xlsx | Row # is the Excel row (header is row 1) | Code |  | Not Run
REV-003 | Review & Validate and Submit | Review | Error reasons listed per row | Functional | P1 | - | 1. Open the Errors tab | VALIDATION_all_cases_invoice_upload.xlsx | Each error row shows every reason as a list; expected messages are on the file's 'Expected Results' sheet | Code |  | Not Run
REV-004 | Review & Validate and Submit | Review | Blank row is skipped | Functional | P3 | - | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx | VALIDATION_all_cases_invoice_upload.xlsx | The completely empty row is not counted | Code |  | Not Run
REV-005 | Review & Validate and Submit | Review | Empty state | UI/UX | P4 | Nothing uploaded | 1. Open Review & Validate from the menu | - | 'Nothing to review yet' with a Go to Invoice Upload button | Code |  | Not Run
REV-006 | Review & Validate and Submit | Review | Loading skeleton | UI/UX | P4 | Slow network | 1. Open Review with throttled network | - | Skeleton of title, tiles and table | Code |  | Not Run
REV-007 | Review & Validate and Submit | Review | Opens the latest upload when nothing is selected | Functional | P3 | Uploads exist | 1. Click Review & Validate in the menu | - | The most recent upload is shown | Code |  | Not Run
REV-008 | Review & Validate and Submit | Review | Paging 50 rows per page | Functional | P3 | A file with more than 50 rows | 1. Upload file_level_checks/07_5000_rows.xlsx 2. Use the pager | 07_5000_rows.xlsx | 50 rows per page; 'Showing x to y of z' correct | Code |  | Not Run
REV-009 | Review & Validate and Submit | Submit | Submit button is in the header | UI/UX | P1 | Valid rows present | 1. Look at the top right of the page | - | 'Submit N Records' next to the file name and Replace; visible without scrolling | Code |  | Not Run
REV-010 | Review & Validate and Submit | Submit | Submit saves the valid rows | Functional | P1 | 41 valid rows | 1. Click Submit | ALL_CASES_invoice_upload_TDS2pct.xlsx | Opens Invoice List; 41 invoices exist; invoice_tds has 41 rows; each import row has created_invoice_id; upload is CONFIRMED | Code |  | Not Run
REV-011 | Review & Validate and Submit | Submit | Invoices link to customer and site | Integration | P1 | After Submit | 1. Run the join query from the Database Checks module | - | Every invoice has a customer, a site, a branch and an invoice_tds row | Code |  | Not Run
REV-012 | Review & Validate and Submit | Submit | Error rows are never saved | Functional | P1 | Mixed file | 1. Submit 2. Open Invoice List | VALIDATION_all_cases_invoice_upload.xlsx | Only valid rows exist as invoices | Code |  | Not Run
REV-013 | Review & Validate and Submit | Submit | Submit disabled when nothing is valid | Functional | P2 | No valid rows | 1. Open Review | - | Submit is disabled | Code |  | Not Run
REV-014 | Review & Validate and Submit | Submit | Submit twice | Negative | P1 | Already submitted | 1. Open the same review again | - | Button reads 'Submitted' and is disabled; API says 'This import has already been imported.' | Code |  | Not Run
REV-015 | Review & Validate and Submit | Submit | Double click on Submit | Negative | P2 | - | 1. Double-click Submit | - | Only one set of invoices is created (button shows 'Submitting…' and is disabled) | Standard |  | Not Run
REV-016 | Review & Validate and Submit | Submit | A row becomes a duplicate after upload | Negative | P3 | Upload previewed | 1. Create the same invoice another way 2. Click Submit | - | Row skipped with a reason; message '… submitted. … row(s) were skipped' | Code |  | Not Run
REV-017 | Review & Validate and Submit | Submit | All-or-nothing | Integration | P2 | - | 1. Force a database error during Submit (e.g. stop MySQL mid-way) | - | Nothing is half saved; Submit can be retried | Code |  | Not Run
REV-018 | Review & Validate and Submit | Submit | Bell notification after Submit | Integration | P3 | - | 1. Submit 2. Open the bell | - | Notification with the file name and counts; clicking it opens Review | Code |  | Not Run
REV-019 | Review & Validate and Submit | Errors | Download error rows | Functional | P2 | Errors exist | 1. Click Download Error Rows | VALIDATION_all_cases_invoice_upload.xlsx | CSV with only failed rows and their reasons | Code |  | Not Run
REV-020 | Review & Validate and Submit | Replace | Replace the file | Functional | P3 | - | 1. Click Replace 2. Upload another file | - | Back to upload; the new file is reviewed | Code |  | Not Run
REV-021 | Review & Validate and Submit | Back | Back arrow returns to upload | Functional | P4 | - | 1. Click the arrow next to the title | - | Invoice Upload opens | Code |  | Not Run
REV-022 | Review & Validate and Submit | Review | Another user's upload | Security | P1 | Upload made by another user | 1. Open /accountant/invoices/review?import=<their id> | - | 'Import not found'; nothing shown | Code |  | Not Run
REV-023 | Review & Validate and Submit | Review | Icons and layout | UI/UX | P4 | - | 1. Look at the page | - | Icons on title, tiles, tabs and buttons; Download Error Rows at the bottom; no button under the taskbar | Code |  | Not Run
ROW-001 | Row Validation (per row of the upload) | Validation row | Invoice number empty | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx - row 'Invoice number empty' | 'Invoice number is required' | Code |  | Not Run
ROW-002 | Row Validation (per row of the upload) | Validation row | Invoice number only spaces | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice number is required' | Code |  | Not Run
ROW-003 | Row Validation (per row of the upload) | Validation row | Invoice number 100 characters | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-004 | Row Validation (per row of the upload) | Validation row | Invoice number 101 characters | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice number is too long (maximum 100 characters)' | Code |  | Not Run
ROW-005 | Row Validation (per row of the upload) | Validation row | Invoice number with special characters (/ # ( ) & ü) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-006 | Row Validation (per row of the upload) | Validation row | Customer empty | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Customer is required' | Code |  | Not Run
ROW-007 | Row Validation (per row of the upload) | Validation row | Customer does not exist | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Customer not found in the system' | Code |  | Not Run
ROW-008 | Row Validation (per row of the upload) | Validation row | Customer typed as its code (SLL12) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid; matched to Silverline | Code |  | Not Run
ROW-009 | Row Validation (per row of the upload) | Validation row | Customer in capitals with spaces, site in lower case | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-010 | Row Validation (per row of the upload) | Validation row | Two customers with the same name (Twin Traders) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'More than one customer has this name. Please use the customer code' | Code |  | Not Run
ROW-011 | Row Validation (per row of the upload) | Validation row | Same name resolved by code (TWN07A / twn07b) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-012 | Row Validation (per row of the upload) | Validation row | Inactive customer (Dormant Stores Ltd) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Customer is inactive' | Code |  | Not Run
ROW-013 | Row Validation (per row of the upload) | Validation row | Unicode (Kannada) customer and site | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-014 | Row Validation (per row of the upload) | Validation row | Apostrophe customer (D'Souza) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-015 | Row Validation (per row of the upload) | Validation row | Very long customer name (195 characters) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-016 | Row Validation (per row of the upload) | Validation row | Site empty | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Site is required' | Code |  | Not Run
ROW-017 | Row Validation (per row of the upload) | Validation row | Site does not exist | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Site not found for this customer' | Code |  | Not Run
ROW-018 | Row Validation (per row of the upload) | Validation row | Site belongs to another customer | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Site not found for this customer' | Code |  | Not Run
ROW-019 | Row Validation (per row of the upload) | Validation row | Inactive site (Ambar - Godown B (closed)) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Site is inactive' | Code |  | Not Run
ROW-020 | Row Validation (per row of the upload) | Validation row | Site in another branch (Southern - Depot, Brightside - Annex) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx - accountant of Head Office | 'This site belongs to another branch, so you cannot create invoices for it' | Code |  | Not Run
ROW-021 | Row Validation (per row of the upload) | Validation row | Comma inside a site name | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-022 | Row Validation (per row of the upload) | Validation row | Invoice date empty | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice date is required' | Code |  | Not Run
ROW-023 | Row Validation (per row of the upload) | Validation row | Date as text yyyy-mm-dd, dd/mm/yyyy, dd-mm-yyyy, d/m/yyyy | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid (4 rows) | Code |  | Not Run
ROW-024 | Row Validation (per row of the upload) | Validation row | Date 31/02/2026, 2026/09/01, 31-31-2026, 00/00/0000, 2026-13-01, 'today', 01.09.2026, 1/9/26 | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Each: 'Invoice date is not valid (use DD/MM/YYYY or YYYY-MM-DD)' | Code |  | Not Run
ROW-025 | Row Validation (per row of the upload) | Validation row | A plain number typed in the date column | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice date is not valid …' | Code |  | Not Run
ROW-026 | Row Validation (per row of the upload) | Validation row | Leap day 29/02/2028 and year 2000 dates | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-027 | Row Validation (per row of the upload) | Validation row | Due date empty (optional) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-028 | Row Validation (per row of the upload) | Validation row | Due date same as invoice date | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-029 | Row Validation (per row of the upload) | Validation row | Due date before invoice date | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Due date cannot be before the invoice date' | Code |  | Not Run
ROW-030 | Row Validation (per row of the upload) | Validation row | Due date text ('tomorrow') | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Due date is not valid (use DD/MM/YYYY or YYYY-MM-DD)' | Code |  | Not Run
ROW-031 | Row Validation (per row of the upload) | Validation row | Amount empty | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice amount is required' | Code |  | Not Run
ROW-032 | Row Validation (per row of the upload) | Validation row | Amounts 0.01, 1, 9999999999999.99 | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-033 | Row Validation (per row of the upload) | Validation row | Amounts written as ₹ 1,20,000 / Rs. 5,000.50 / 12,50,000 / ' 4500 ' / '100 000' | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid (5 rows) | Code |  | Not Run
ROW-034 | Row Validation (per row of the upload) | Validation row | Amount 0 and -1 | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice amount must be greater than 0' | Code |  | Not Run
ROW-035 | Row Validation (per row of the upload) | Validation row | Amount abc, 1e5, $500, 1.234.567,89 | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice amount is not a valid number' | Code |  | Not Run
ROW-036 | Row Validation (per row of the upload) | Validation row | Amount 10000000000000 | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Invoice amount is too large' | Code |  | Not Run
ROW-037 | Row Validation (per row of the upload) | Validation row | Remarks empty (optional) | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-038 | Row Validation (per row of the upload) | Validation row | Remarks 1000 characters, unicode and emoji | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid | Code |  | Not Run
ROW-039 | Row Validation (per row of the upload) | Validation row | Same invoice number twice, same customer | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | 'Duplicate invoice number: also used on row N of this file' on the second row | Code |  | Not Run
ROW-040 | Row Validation (per row of the upload) | Validation row | Same number in lower case | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Also a duplicate (case ignored) | Code |  | Not Run
ROW-041 | Row Validation (per row of the upload) | Validation row | Duplicate found through the customer code | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Also a duplicate | Code |  | Not Run
ROW-042 | Row Validation (per row of the upload) | Validation row | Same number for a different customer | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | Valid (unique per customer only) | Code |  | Not Run
ROW-043 | Row Validation (per row of the upload) | Validation row | Invoice already saved in the system | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx - submit ALL_CASES_invoice_upload_TDS2pct.xlsx first | 'Duplicate invoice number: this customer already has this invoice' | Code |  | Not Run
ROW-044 | Row Validation (per row of the upload) | Validation row | Several errors in one row | Validation | P1 | Customers and sites of the test data exist | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Open Review & Validate 3. Find the row | VALIDATION_all_cases_invoice_upload.xlsx | All reasons listed (e.g. 3 reasons or 2 reasons) | Code |  | Not Run
ROW-045 | Row Validation (per row of the upload) | Edge file | Amount 0.001 passes review | Boundary | P3 | - | 1. Upload EDGE_rows_to_observe.xlsx 2. Submit only the rows you want to observe | EDGE_rows_to_observe.xlsx | Review says valid; check what amount is saved (database keeps 2 decimals) and report | Standard |  | Not Run
ROW-046 | Row Validation (per row of the upload) | Edge file | Remarks of 1001 characters | Boundary | P3 | - | 1. Upload EDGE_rows_to_observe.xlsx | EDGE_rows_to_observe.xlsx | Passes review; check what Submit does with a remark longer than the database column (1000) and report | Standard |  | Not Run
ROW-047 | Row Validation (per row of the upload) | Edge file | Far future dates (31/12/2099) | Boundary | P4 | - | 1. Upload EDGE_rows_to_observe.xlsx | EDGE_rows_to_observe.xlsx | Accepted; dates display correctly | Standard |  | Not Run
INV-001 | Invoice List & Invoice Details | List | Columns | UI/UX | P2 | Invoices exist | 1. Open Invoice List | - | Invoice No, Date, Due Date, Customer (with site), Invoice Amount, Paid, Pending, Status, Action (eye) | Code |  | Not Run
INV-002 | Invoice List & Invoice Details | List | Tabs filter by status | Functional | P1 | Invoices in every status | 1. Click All, Pending, Overdue, Partially Paid, Paid | FIVE_STATUS_invoice_upload.xlsx | Each tab lists only its status | Code |  | Not Run
INV-003 | Invoice List & Invoice Details | List | Search by invoice number or customer | Functional | P2 | - | 1. Type part of a number 2. Type part of a customer | 'BSPMPL', 'Cadabams' | Matching rows only | Code |  | Not Run
INV-004 | Invoice List & Invoice Details | List | Customer, date and status filters | Functional | P2 | - | 1. Use each filter and combine them | - | Rows satisfy every filter | Code |  | Not Run
INV-005 | Invoice List & Invoice Details | List | Paid column includes TDS | Functional | P2 | Payment with TDS | 1. Pay cash 49,000 + TDS 1,000 on 50,000 | - | Paid shows 50,000; Pending 0 | Code |  | Not Run
INV-006 | Invoice List & Invoice Details | List | Pagination | Functional | P3 | More than 10 invoices | 1. Go through the pages | ALL_CASES_invoice_upload_TDS2pct.xlsx | 10 per page; 'Showing x to y of z' correct | Code |  | Not Run
INV-007 | Invoice List & Invoice Details | List | Export to CSV | Functional | P2 | Rows visible | 1. Click Export | - | CSV of the filtered rows; button disabled when there are none | Code |  | Not Run
INV-008 | Invoice List & Invoice Details | List | Empty state and skeleton | UI/UX | P4 | - | 1. Open with no invoices / slow network | - | 'No invoices found'; pulsing rows while loading | Code |  | Not Run
INV-009 | Invoice List & Invoice Details | List | Only own-branch invoices | Security | P1 | - | 1. Compare with the database | - | No invoice of another branch's site | Code |  | Not Run
INV-010 | Invoice List & Invoice Details | Details | Open an invoice (eye icon) | Functional | P1 | - | 1. Click the eye icon | - | Details page with amounts, dates, customer, site | Code |  | Not Run
INV-011 | Invoice List & Invoice Details | Details | Four amount tiles | Functional | P2 | - | 1. Read the tiles | - | Invoice Amount, Paid Amount, Pending Amount, Due Date | Code |  | Not Run
INV-012 | Invoice List & Invoice Details | Details | Remarks appear in Invoice Information | Functional | P2 | Invoice with a remark | 1. Open the invoice | - | Remarks line shows the text from the Excel file; '—' when empty | Code |  | Not Run
INV-013 | Invoice List & Invoice Details | Details | Payment History has Cash and TDS columns | Functional | P2 | Payment recorded | 1. Open the invoice | - | Date, Cash, TDS, Mode, UTR No, Received By | Code |  | Not Run
INV-014 | Invoice List & Invoice Details | Details | TDS Information card | Functional | P1 | TDS customer | 1. Open the invoice | - | Rate, Expected, Deducted, Pending TDS, status and TDS history (Current / Previous) | Code |  | Not Run
INV-015 | Invoice List & Invoice Details | Details | Non-TDS customer | Functional | P2 | Customer without TDS | 1. Open the invoice | - | 'TDS is not applicable for this invoice.' | Code |  | Not Run
INV-016 | Invoice List & Invoice Details | Details | Record Payment button state | Functional | P3 | - | 1. Open a pending and a paid invoice | - | Enabled when something is pending; disabled when paid or cancelled; opens Record Payment with the customer chosen | Code |  | Not Run
INV-017 | Invoice List & Invoice Details | Details | Add Task | Functional | P2 | - | 1. Click Add Task 2. Fill and save | - | Reminder saved; appears in Follow-up History | Code |  | Not Run
INV-018 | Invoice List & Invoice Details | Details | Call Customer is disabled | Functional | P4 | - | 1. Point at Call Customer | - | Disabled (no phone stored for customers) | Code |  | Not Run
INV-019 | Invoice List & Invoice Details | Details | Unknown or other-branch invoice | Security | P1 | - | 1. Open /accountant/invoices/<random id> | - | Not found; nothing shown | Code |  | Not Run
INV-020 | Invoice List & Invoice Details | Details | Breadcrumb | UI/UX | P4 | - | 1. Click 'Invoices' at the top | - | Back to Invoice List | Code |  | Not Run
STS-001 | Invoice Status (five statuses) | Rules | New invoice status | Functional | P1 | - | 1. Submit an upload 2. Check the database | ALL_CASES_invoice_upload_TDS2pct.xlsx | Every new invoice is stored PENDING with paid 0 and pending = amount (or OVERDUE if already late) | Code |  | Not Run
STS-002 | Invoice Status (five statuses) | Rules | Pending shown for a not-yet-due invoice | Functional | P1 | Invoice with a future due date | 1. Open Invoice List | FIVE_STATUS_invoice_upload.xlsx (…/2898) | Badge Pending; database PENDING | Code |  | Not Run
STS-003 | Invoice Status (five statuses) | Rules | Overdue shown for a late unpaid invoice | Functional | P1 | Due date in the past | 1. Open Invoice List | FIVE_STATUS_invoice_upload.xlsx (…/040) | Badge Overdue; database status OVERDUE (not PENDING) | Code |  | Not Run
STS-004 | Invoice Status (five statuses) | Rules | Partially Paid | Functional | P1 | Future due date | 1. Pay part of the invoice (cash 5,000 on 12,980) | FIVE_STATUS_invoice_upload.xlsx (…/05889) | Status PARTIAL in the database and 'Partially Paid' on screen; pending 7,980 | Code |  | Not Run
STS-005 | Invoice Status (five statuses) | Rules | Paid | Functional | P1 | - | 1. Pay the full amount (cash 10,499) | FIVE_STATUS_invoice_upload.xlsx (…/1233) | Status PAID; pending 0 | Code |  | Not Run
STS-006 | Invoice Status (five statuses) | Rules | Cash plus TDS settles the invoice | Functional | P1 | TDS customer | 1. Pay cash 49,000 + TDS 1,000 on 50,000 | - | PAID; TDS status CLEARED | Code |  | Not Run
STS-007 | Invoice Status (five statuses) | Rules | Cancelled | Functional | P1 | Unpaid invoice | 1. Cancel the invoice (see the note on the missing button) | FIVE_STATUS_invoice_upload.xlsx (…/3456) | Status CANCELLED; excluded from totals; cannot take payments | Code |  | Not Run
STS-008 | Invoice Status (five statuses) | Rules | Cancel an invoice that has a payment | Negative | P1 | Payment recorded | 1. Call the cancel action | - | 'Cannot cancel an invoice that already has payments allocated to it' | Code |  | Not Run
STS-009 | Invoice Status (five statuses) | Rules | Cancel twice | Negative | P3 | Already cancelled | 1. Cancel again | - | 'Invoice is already cancelled' | Code |  | Not Run
STS-010 | Invoice Status (five statuses) | Known gap | No Cancel button in the accountant panel | Functional | P2 | - | 1. Open Invoice Details | - | Only Record Payment, Add Task and Call Customer exist; cancelling needs an admin screen or a code change. Record the decision. | Code |  | Not Run
STS-011 | Invoice Status (five statuses) | Stored = shown | Database status equals the screen | Integration | P1 | Invoices in all statuses | 1. Compare Invoice List with phpMyAdmin invoices.status | - | Same status on both, for every invoice | Code |  | Not Run
STS-012 | Invoice Status (five statuses) | Sync | Sync runs when the backend starts | Integration | P1 | Late invoices stored as PENDING | 1. Restart the backend 2. Check the log and the table | - | Log line 'Invoice status sync: n marked OVERDUE'; those invoices are OVERDUE | Code |  | Not Run
STS-013 | Invoice Status (five statuses) | Sync | Sync runs after Submit, payment, create and edit | Integration | P1 | - | 1. Submit an upload with past due dates 2. Pay part of a late invoice | - | Late invoices are OVERDUE immediately; a part-paid late invoice stays OVERDUE | Code |  | Not Run
STS-014 | Invoice Status (five statuses) | Sync | Daily job at 00:05 | Integration | P2 | An invoice due today | 1. Wait until after midnight (or move the server date) | - | It becomes OVERDUE the next day | Code |  | Not Run
STS-015 | Invoice Status (five statuses) | Sync | Extending a due date restores the status | Functional | P2 | OVERDUE invoice | 1. Change its due date to a future date (admin/API) | - | Back to PENDING (or PARTIAL if something was paid) | Code |  | Not Run
STS-016 | Invoice Status (five statuses) | Sync | PAID and CANCELLED are never touched | Functional | P1 | - | 1. Run the sync with paid and cancelled invoices | - | Their status does not change | Code |  | Not Run
STS-017 | Invoice Status (five statuses) | Sync | Fully paying an OVERDUE invoice | Functional | P1 | OVERDUE invoice | 1. Pay the whole pending amount | - | PAID | Code |  | Not Run
STS-018 | Invoice Status (five statuses) | Sync | Part-paying an OVERDUE invoice | Functional | P1 | OVERDUE invoice | 1. Pay part of it | - | Stays OVERDUE (paid_amount shows what was paid) | Code |  | Not Run
STS-019 | Invoice Status (five statuses) | Rules | PAID never reopens | Functional | P1 | PAID invoice with pending TDS | 1. Add previous TDS on a later payment | - | Invoice stays PAID; only the TDS status changes | Code |  | Not Run
STS-020 | Invoice Status (five statuses) | Rules | Past-due Pending and Partial look Overdue | Functional | P2 | Due date passed | 1. Look at Invoice List | - | Shown as Overdue (to see Pending or Partially Paid, the due date must be in the future) | Code |  | Not Run
STS-021 | Invoice Status (five statuses) | Scenario | Five invoices, five statuses | Integration | P1 | Customers of the FIVE_STATUS file exist | 1. Upload and Submit FIVE_STATUS_invoice_upload.xlsx 2. Pay …/05889 5,000 and …/1233 10,499 3. Cancel …/3456 | FIVE_STATUS_invoice_upload.xlsx | Overdue, Partially Paid, Paid, Cancelled, Pending - one each; database matches | Code |  | Not Run
OUT-001 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Five summary tiles | Functional | P1 | Unpaid invoices exist | 1. Open Outstanding | - | Total Outstanding, Overdue Amount, Due This Week, Unpaid Invoices, Avg. Days Overdue | Code |  | Not Run
OUT-002 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Only unpaid, non-cancelled invoices | Functional | P1 | - | 1. Compare with Invoice List | - | PAID and CANCELLED invoices are absent; sorted most overdue first | Code |  | Not Run
OUT-003 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Chips and their counts | Functional | P2 | Invoices due at different times | 1. Click All Unpaid, Overdue, Due Today, Due This Week, Due This Month, No Follow-up Set | ALL_CASES_invoice_upload_TDS2pct.xlsx | Counts in brackets match the rows shown | Code |  | Not Run
OUT-004 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Ageing and minimum pending filters | Functional | P3 | - | 1. Choose an ageing bucket 2. Type a minimum pending amount | - | Rows narrow accordingly | Code |  | Not Run
OUT-005 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Days overdue column | Functional | P2 | Invoice due 30/05/2019 | 1. Read the row | - | Days late = today - due date | Code |  | Not Run
OUT-006 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Follow-up column | Functional | P3 | A reminder on an invoice | 1. Read the row | - | Next follow-up date; 'No follow-up set' when none | Code |  | Not Run
OUT-007 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Record payment and reminder icons | Functional | P3 | - | 1. Click each icon on a row | - | Record Payment opens for the customer; reminder dialog opens | Code |  | Not Run
OUT-008 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Bulk reminder | Functional | P3 | 3 rows ticked | 1. Click Add Reminder | - | One task per invoice created | Code |  | Not Run
OUT-009 | Outstanding, Customer Outstanding & Payment Tracking | Outstanding | Export | Functional | P3 | - | 1. Click Export | - | CSV of the filtered rows | Code |  | Not Run
OUT-010 | Outstanding, Customer Outstanding & Payment Tracking | Customer Outstanding | Tiles and table (open by URL) | Functional | P2 | - | 1. Open /accountant/payments/customer-outstanding | - | Total Outstanding, Customers With Dues, Overdue Amount, Avg. per Customer, Highest Outstanding; one row per customer with dues | Code |  | Not Run
OUT-011 | Outstanding, Customer Outstanding & Payment Tracking | Customer Outstanding | Expand a customer | Functional | P3 | - | 1. Click the arrow on a row | - | That customer's unpaid invoices listed | Code |  | Not Run
OUT-012 | Outstanding, Customer Outstanding & Payment Tracking | Payment Tracking | Tiles (open by URL) | Functional | P2 | - | 1. Open /accountant/invoices/tracking | - | Total Invoiced, Collected, Pending, Overdue, Collection Rate (%) | Code |  | Not Run
OUT-013 | Outstanding, Customer Outstanding & Payment Tracking | Payment Tracking | Filters and export | Functional | P3 | - | 1. Filter by status, customer, due-date range 2. Export | - | Rows and CSV match the filters; CSV has Last Payment and Next Follow-up | Code |  | Not Run
PAY-001 | Record Payment | Layout | Page structure | UI/UX | P2 | - | 1. Open Record Payment | - | 1 Select Customer, 2 Select Invoices, 3 Payment Details (side by side), 4 Payment Summary, 5 Recent Payments; no breadcrumb | Code |  | Not Run
PAY-002 | Record Payment | Customer | Customer stats box | Functional | P1 | - | 1. Choose a customer | Bluewave Hotels Pvt Ltd | Total Invoiced, Total Paid, Outstanding, Oldest Due, Total Invoices, Overdue Invoices match the invoices; cancelled ones excluded | Code |  | Not Run
PAY-003 | Record Payment | Customer | TDS Applicable badge | Functional | P2 | - | 1. Choose a TDS customer, then a non-TDS one | BWH01 vs SAO02 | Green 'TDS Applicable (2%)' badge only for the TDS customer | Code |  | Not Run
PAY-004 | Record Payment | Customer | Customer list shows name and code | UI/UX | P4 | - | 1. Open the customer dropdown | - | 'Name (CODE)' when a code exists, otherwise just the name | Code |  | Not Run
PAY-005 | Record Payment | Customer | Pre-selected from an invoice | Functional | P4 | - | 1. Invoice Details > Record Payment | - | Customer already chosen | Code |  | Not Run
PAY-006 | Record Payment | Invoices | Oldest first, only unpaid by default | Functional | P2 | - | 1. Choose a customer | - | Unpaid invoices, oldest due first; 'Show fully paid invoices' adds the paid ones | Code |  | Not Run
PAY-007 | Record Payment | Invoices | TDS columns only for TDS customers | UI/UX | P1 | - | 1. Choose a TDS customer, then a non-TDS one | - | TDS Rate, TDS Pending, TDS Amount, Total Allocation shown only for the TDS customer | Code |  | Not Run
PAY-008 | Record Payment | Invoices | Table fits on laptop screens | Responsive | P3 | TDS customer, 1366 px wide | 1. Look at the table | - | Cash and TDS boxes visible without sideways scrolling (Invoice Date, TDS Rate, Total Allocation and Status are hidden at this width) | Code |  | Not Run
PAY-009 | Record Payment | Invoices | Inputs are disabled until the invoice is ticked | Functional | P1 | - | 1. Try typing in Cash Amount before ticking | - | Boxes are greyed out; ticking the invoice enables them | Code |  | Not Run
PAY-010 | Record Payment | Invoices | Ticking suggests the amounts | Functional | P2 | TDS customer, cash received typed | 1. Tick an invoice | - | TDS = pending TDS; cash = what is left of the cash received (up to the pending amount) | Code |  | Not Run
PAY-011 | Record Payment | Invoices | Select all | Functional | P3 | - | 1. Tick the header checkbox | - | All payable invoices ticked, cash spread oldest first | Code |  | Not Run
PAY-012 | Record Payment | Add Previous TDS | Button state when nothing qualifies | Functional | P1 | TDS customer, no fully paid invoice with pending TDS | 1. Look at the button and hover it | - | Disabled (grey); hint 'No earlier invoice has pending TDS' | Code |  | Not Run
PAY-013 | Record Payment | Add Previous TDS | Button disabled for a non-TDS customer | Functional | P2 | - | 1. Choose a non-TDS customer | - | Disabled; hint 'TDS is not applicable for this customer' | Code |  | Not Run
PAY-014 | Record Payment | Add Previous TDS | Enabled once an invoice is fully paid without TDS | Functional | P1 | TDS customer | 1. Pay an invoice in full in cash with TDS 0 2. Open Record Payment again | Lotus ALL-2026-031: cash 15,000, TDS 0 | Button turns blue; the dialog lists the invoice with its pending TDS (300) | Code |  | Not Run
PAY-015 | Record Payment | Add Previous TDS | Apply previous TDS | Functional | P1 | Button enabled | 1. Open the dialog 2. Tick the invoice, keep 300 3. Apply 4. Add cash for another invoice of the same customer 5. Save | - | TDS type PREVIOUS saved; the paid invoice stays PAID; its TDS becomes CLEARED | Code |  | Not Run
PAY-016 | Record Payment | Add Previous TDS | More than the pending TDS | Negative | P1 | - | 1. Enter 500 when 300 is pending | - | Blocked in the dialog ('more than its pending TDS') | Code |  | Not Run
PAY-017 | Record Payment | Add Previous TDS | Previous TDS cannot be the only thing in a payment | Negative | P2 | - | 1. Apply only previous TDS with Cash Received 0 2. Save | - | 'Please enter the cash received.' | Code |  | Not Run
PAY-018 | Record Payment | Payment details | Fields and labels | UI/UX | P2 | - | 1. Look at section 3 | - | Payment Date, Payment Mode, UTR No (placeholder 'Enter UTR number'), Cash Received, Remarks; Cancel and Save Payment | Code |  | Not Run
PAY-019 | Record Payment | Payment details | UTR No label everywhere | UI/UX | P3 | - | 1. Check the form and the Recent Payments table | - | 'UTR No' (no 'Reference No') | Code |  | Not Run
PAY-020 | Record Payment | Payment details | Payment modes | Functional | P3 | - | 1. Save one payment per mode | Cash, UPI, Bank Transfer, NEFT, Cheque, Card, Other | Each saved and shown with its label | Code |  | Not Run
PAY-021 | Record Payment | Payment details | Payment date defaults to today | UI/UX | P4 | - | 1. Open the page | - | Today's date; can be changed | Code |  | Not Run
PAY-022 | Record Payment | Save | Full cash payment | Functional | P1 | Unpaid invoice | 1. Cash received 10,499 2. Tick the invoice 3. Save Payment | FIVE_STATUS_invoice_upload.xlsx (…/1233) | Opens Payment List with the new payment; invoice PAID; pending 0 | Code |  | Not Run
PAY-023 | Record Payment | Save | Partial payment | Functional | P1 | - | 1. Cash 5,000 on 12,980 | FIVE_STATUS_invoice_upload.xlsx (…/05889) | PARTIAL; pending 7,980 | Code |  | Not Run
PAY-024 | Record Payment | Save | One payment for several invoices | Functional | P1 | 3 invoices of one customer | 1. Tick all three 2. Enter cash and TDS for each 3. Save | ALL_CASES payment P09 | One payment, three allocations; each invoice updated | Code |  | Not Run
PAY-025 | Record Payment | Save | Advance / unallocated cash | Functional | P2 | - | 1. Cash received 20,000, allocate 14,700 + TDS 300 | ALL_CASES payment P10 | Payment List shows 5,300 unallocated | Code |  | Not Run
PAY-026 | Record Payment | Save | Rounding | Boundary | P2 | - | 1. Cash 32,666.34 + TDS 666.66 on 33,333 | ALL_CASES payment P12 | Invoice PAID exactly; totals to 2 decimals | Code |  | Not Run
PAY-027 | Record Payment | Save | Double click on Save | Negative | P1 | - | 1. Double-click Save Payment | - | One payment only ('Saving…', button disabled) | Standard |  | Not Run
PAY-028 | Record Payment | Save | Cancel | Functional | P4 | - | 1. Fill the form 2. Cancel | - | Back to Payment List; nothing saved | Code |  | Not Run
PAY-029 | Record Payment | Summary | Four tiles | Functional | P2 | Invoices allocated | 1. Read Payment Summary | - | Cash Received, Total TDS Deducted, Total Settlement (cash allocated + TDS), Invoices Allocated | Code |  | Not Run
PAY-030 | Record Payment | Recent | Recent Payments for this customer | Functional | P3 | Payments exist | 1. Choose a customer | - | Last 5 payments with date, UTR No, cash, TDS, mode, allocated, remarks, created by | Code |  | Not Run
PAY-031 | Record Payment | Validation | No customer | Validation | P1 | - | 1. Click Save without a customer | - | 'Please select a customer.' | Code |  | Not Run
PAY-032 | Record Payment | Validation | Cash received empty or 0 | Validation | P1 | - | 1. Save with 0 | - | 'Please enter the cash received.' | Code |  | Not Run
PAY-033 | Record Payment | Validation | No invoice ticked | Validation | P1 | - | 1. Enter cash, tick nothing, Save | - | 'Tick at least one invoice and enter an amount.' | Code |  | Not Run
PAY-034 | Record Payment | Validation | Cash allocated more than cash received | Negative | P1 | - | 1. Received 10,000, allocate 12,000 | - | 'The cash allocated is more than the cash received.' | Code |  | Not Run
PAY-035 | Record Payment | Validation | Cash plus TDS more than the pending amount | Negative | P1 | Pending 30,000 | 1. Cash 29,500 + TDS 600 | - | 'Cash plus TDS for <invoice> is more than its pending amount.' | Code |  | Not Run
PAY-036 | Record Payment | Validation | Cash on a fully paid invoice | Negative | P1 | Paid invoice with pending TDS | 1. Enter cash on it | - | '<invoice> is already paid. Only TDS can be added to it.' | Code |  | Not Run
PAY-037 | Record Payment | Validation | TDS for a non-TDS customer | Negative | P1 | - | 1. Send TDS through the API | - | 'TDS is not applicable for invoice …' (the box is disabled on screen) | Code |  | Not Run
PAY-038 | Record Payment | Validation | Negative amounts | Negative | P2 | - | 1. Type -100 | - | 'Amounts cannot be negative.' | Code |  | Not Run
PAY-039 | Record Payment | Validation | Same invoice twice (API) | Negative | P2 | - | 1. Send the same invoice id twice | - | 'The same invoice appears more than once' | Code |  | Not Run
PAY-040 | Record Payment | Validation | Another branch's customer | Security | P1 | - | 1. POST a payment for a customer of branch abc | - | 403 'Cannot record a payment for another branch's customer' | Code |  | Not Run
PAY-041 | Record Payment | Validation | Concurrent payments on one invoice | Performance | P1 | Pending 10,000 | 1. Two users each pay 10,000 at once | - | Only one fully succeeds; the invoice is never over-paid | Code |  | Not Run
PAY-042 | Record Payment | Errors | Save error message | Negative | P3 | Backend stopped | 1. Click Save Payment | - | Red message in the form; nothing lost; can retry | Code |  | Not Run
PLS-001 | Payment List | List | Columns and status | Functional | P1 | Payments exist | 1. Open Payment List | - | Payment No, Date, Customer, Mode, UTR No, Received, Allocated, Unallocated, Status (Posted), Created By | Code |  | Not Run
PLS-002 | Payment List | List | Only cash is shown (TDS is not) | Functional | P2 | Payment with TDS | 1. Read the row and expand it | cash 12,000 + TDS 2,600 | Received and Allocated show cash only; the expanded box shows cash per invoice; TDS is on the invoice details page. Record as a gap if TDS must show here. | Code |  | Not Run
PLS-003 | Payment List | List | Five tiles | Functional | P2 | - | 1. Compare the tiles with the table | - | Total Received, Received This Month, Payments, Unallocated (Advance), Cancelled | Code |  | Not Run
PLS-004 | Payment List | List | Filters and search | Functional | P2 | - | 1. Search payment no / customer / UTR 2. Filter by customer, mode, status, dates | - | Matching rows only; the total row updates | Code |  | Not Run
PLS-005 | Payment List | List | Expand a payment | Functional | P2 | - | 1. Click the arrow | - | 'Allocated to invoices' with invoice links and remarks | Code |  | Not Run
PLS-006 | Payment List | List | Invoice link opens the invoice | Functional | P3 | - | 1. Click an invoice number in the expanded box | - | Invoice Details opens | Code |  | Not Run
PLS-007 | Payment List | List | Pagination and export | Functional | P3 | - | 1. Page through 2. Export | - | 10 per page; CSV of the filtered rows | Code |  | Not Run
PLS-008 | Payment List | List | Total row excludes cancelled payments | Functional | P3 | - | 1. Read the footer | - | 'Total for all n rows shown (cancelled payments excluded)' | Code |  | Not Run
PLS-009 | Payment List | List | Empty and loading states | UI/UX | P4 | - | 1. Open with no payments / slow network | - | 'No payments found'; placeholder rows while loading | Code |  | Not Run
PLS-010 | Payment List | Database | Payment rows written correctly | Integration | P1 | After a payment with TDS | 1. Check payments, payment_allocations and tds_transactions | - | 1 payment (cash + TDS total), one allocation per invoice, one tds_transactions row per TDS line (CURRENT or PREVIOUS) | Code |  | Not Run
TDS-001 | TDS | Menu | TDS item in the sidebar | UI/UX | P3 | - | 1. Look at the sidebar | - | 'TDS' with a percent icon (opens /accountant/settings) | Code |  | Not Run
TDS-002 | TDS | Page | Customer list | Functional | P1 | Customers exist | 1. Open TDS | - | Customer, TDS Applicable, TDS Rate, Pending TDS, Edit | Code |  | Not Run
TDS-003 | TDS | Page | Pending TDS per customer | Functional | P2 | Invoices with TDS pending | 1. Compare with the invoices | - | Sum of pending TDS of the customer's non-cancelled invoices; '—' for customers without TDS | Code |  | Not Run
TDS-004 | TDS | Page | Search | Functional | P4 | - | 1. Type part of a name or code | - | List filters as you type | Code |  | Not Run
TDS-005 | TDS | Edit | Turn TDS on with 2% | Functional | P1 | - | 1. Edit a customer 2. Tick TDS applicable 3. Rate 2 4. Save | - | Saved; list shows Yes and 2% | Code |  | Not Run
TDS-006 | TDS | Edit | Turn TDS off | Functional | P2 | - | 1. Untick TDS applicable 2. Save | - | Shown as No; rate cleared | Code |  | Not Run
TDS-007 | TDS | Edit | Rate boundaries | Boundary | P1 | - | 1. Try 0, 0.01, 2, 100, 100.01, -1, abc, blank | - | 0, blank, 100.01, -1 and abc are rejected ('Enter a TDS rate between 0 and 100'); 0.01, 2 and 100 are accepted | Code |  | Not Run
TDS-008 | TDS | Edit | Only 2% is used in this business | Functional | P2 | - | 1. Check every customer's rate | - | All TDS customers are 2%; the app itself allows 0-100, so confirm nothing else is set | Code |  | Not Run
TDS-009 | TDS | Edit | Apply to existing invoices | Functional | P2 | Invoices with and without deducted TDS | 1. Change the setting 2. Tick 'apply to existing' 3. Save | - | Message shows how many invoices changed; only invoices with no TDS deducted yet change | Code |  | Not Run
TDS-010 | TDS | Edit | Change is not retroactive | Design | P1 | - | 1. Turn TDS off without 'apply to existing' 2. Open an old invoice | - | Old invoice keeps its 2% TDS; new invoices have none | Design |  | Not Run
TDS-011 | TDS | Snapshot | TDS copied at Submit | Design | P1 | TDS set before upload | 1. Submit an upload 2. Open an invoice | ALL_CASES_invoice_upload_TDS2pct.xlsx | invoice_tds row: rate 2, expected = amount x 2% (2 decimals), pending = expected, status PENDING | Code |  | Not Run
TDS-012 | TDS | Snapshot | TDS not set before upload | Design | P2 | Customer without TDS | 1. Submit an upload for it | - | invoice_tds NOT_APPLICABLE; turning TDS on later does not change those invoices unless 'apply to existing' is used | Code |  | Not Run
TDS-013 | TDS | Statuses | TDS status after payments (₹50,000 invoice) | Design | P1 | - | 1. Pay: nothing / cash 20,000 / cash 49,000 + TDS 500 / cash 49,000 + TDS 1,000 | - | PENDING / PENDING / PARTIAL / CLEARED | Code |  | Not Run
TDS-014 | TDS | Statuses | Invoice PAID while TDS PENDING | Design | P1 | - | 1. Pay 50,000 cash with TDS 0 | - | Invoice PAID; TDS PENDING (1,000) | Code |  | Not Run
TDS-015 | TDS | Statuses | Invoice PARTIAL while TDS CLEARED | Design | P2 | - | 1. Cash 5,000 + TDS 200 on a 10,000 invoice (2% = 200) | - | Invoice PARTIAL; TDS CLEARED | Code |  | Not Run
TDS-016 | TDS | Rounding | Odd amounts | Boundary | P2 | - | 1. Check expected TDS for 33,333 / 45,678.90 / 1,234.56 / 8,750.80 | - | 666.66 / 913.58 / 24.69 / 175.02 | Code |  | Not Run
TDS-017 | TDS | Validation | TDS more than pending TDS on a paid invoice | Negative | P1 | - | 1. Try previous TDS above the pending amount | - | 'The TDS for <invoice> is more than its pending TDS.' | Code |  | Not Run
TDS-018 | TDS | Validation | Other-branch customer | Security | P1 | - | 1. PUT tds-settings for a customer of branch abc | - | Not found / forbidden | Code |  | Not Run
TDS-019 | TDS | Database | Settings stored on the customer | Integration | P2 | - | 1. Check companies.tds_applicable and tds_rate after saving | - | Values match what the page shows | Code |  | Not Run
TSK-001 | Tasks & Reminders | Create | Add a reminder from an invoice | Functional | P1 | - | 1. Invoice Details > Add Task 2. Choose type, date, time, priority, notes 3. Save | - | Task created; shown in Follow-up History and Tasks & Reminders | Code |  | Not Run
TSK-002 | Tasks & Reminders | Create | Task types and priorities | Functional | P3 | - | 1. Create tasks of each type and priority | Payment Follow-up, Call Customer, Send Invoice, Send Reminder, Other; Low, Normal, High | Each saved as chosen | Code |  | Not Run
TSK-003 | Tasks & Reminders | Create | Reminder without a date | Validation | P3 | - | 1. Save with no date | - | Saved without a due date, or a clear message | Code |  | Not Run
TSK-004 | Tasks & Reminders | Create | Reminder for several invoices | Functional | P3 | 3 rows ticked on Outstanding | 1. Add Reminder | - | One task per invoice | Code |  | Not Run
TSK-005 | Tasks & Reminders | List | Status Today / Upcoming / Overdue / Completed | Functional | P2 | Tasks with several dates | 1. Open Tasks & Reminders | - | Badge matches the due date and completion | Code |  | Not Run
TSK-006 | Tasks & Reminders | List | Filters and search | Functional | P3 | - | 1. Filter by status and type 2. Search | - | Matching rows only | Code |  | Not Run
TSK-007 | Tasks & Reminders | Complete | Mark a task complete | Functional | P1 | Open task | 1. Click complete | - | COMPLETED with a completed date; shows as last action on Outstanding | Code |  | Not Run
TSK-008 | Tasks & Reminders | Follow-up | Next follow-up on Outstanding | Functional | P2 | - | 1. Open Outstanding | - | Earliest open task date; 'No follow-up set' otherwise | Code |  | Not Run
TSK-009 | Tasks & Reminders | Dashboard | Reminders on the dashboard | Functional | P3 | - | 1. Open Dashboard | - | Upcoming reminders table and Today's Follow-ups tile match | Code |  | Not Run
TSK-010 | Tasks & Reminders | Scoping | Tasks of other branches | Security | P2 | - | 1. Call the tasks API for another branch | - | Not visible | Standard |  | Not Run
TSK-011 | Tasks & Reminders | Errors | Unknown task | Negative | P4 | - | 1. Complete a random task id | - | 'Task not found' | Code |  | Not Run
UIX-001 | Layout, Responsive & Usability | Layout | Header on top, sidebar below | UI/UX | P2 | Laptop | 1. Open any page | - | Full-width header with logo, 'Accountant Panel', bell and user icon; white sidebar with black text below it | Code |  | Not Run
UIX-002 | Layout, Responsive & Usability | Layout | Loading skeletons | UI/UX | P3 | Slow network | 1. Open Invoice List, Outstanding, Payment List | - | Pulsing placeholder rows and tiles, then data | Code |  | Not Run
UIX-003 | Layout, Responsive & Usability | Layout | Icons | UI/UX | P4 | - | 1. Visit each page | - | Icons on headings, tabs, chips, tiles, buttons and search boxes; nothing overlapping | Code |  | Not Run
UIX-004 | Layout, Responsive & Usability | Layout | Date boxes use dd/mm/yyyy | UI/UX | P3 | - | 1. Use the dashboard date boxes | - | Typing digits adds slashes; calendar icon opens the picker | Code |  | Not Run
UIX-005 | Layout, Responsive & Usability | Layout | Empty states | UI/UX | P4 | New branch | 1. Open every list | - | Clear 'No … found' messages; no stuck loading | Code |  | Not Run
UIX-006 | Layout, Responsive & Usability | Responsive | Dashboard at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-007 | Layout, Responsive & Usability | Responsive | Dashboard at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-008 | Layout, Responsive & Usability | Responsive | Dashboard at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-009 | Layout, Responsive & Usability | Responsive | Dashboard at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-010 | Layout, Responsive & Usability | Responsive | Invoice Upload at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/upload 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-011 | Layout, Responsive & Usability | Responsive | Invoice Upload at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/upload 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-012 | Layout, Responsive & Usability | Responsive | Invoice Upload at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/upload 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-013 | Layout, Responsive & Usability | Responsive | Invoice Upload at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/upload 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-014 | Layout, Responsive & Usability | Responsive | Review & Validate at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/review 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-015 | Layout, Responsive & Usability | Responsive | Review & Validate at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/review 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-016 | Layout, Responsive & Usability | Responsive | Review & Validate at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/review 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-017 | Layout, Responsive & Usability | Responsive | Review & Validate at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/review 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-018 | Layout, Responsive & Usability | Responsive | Invoice List at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/list 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-019 | Layout, Responsive & Usability | Responsive | Invoice List at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/list 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-020 | Layout, Responsive & Usability | Responsive | Invoice List at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/list 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-021 | Layout, Responsive & Usability | Responsive | Invoice List at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/list 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-022 | Layout, Responsive & Usability | Responsive | Invoice Details at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/<id> 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-023 | Layout, Responsive & Usability | Responsive | Invoice Details at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/<id> 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-024 | Layout, Responsive & Usability | Responsive | Invoice Details at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/<id> 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-025 | Layout, Responsive & Usability | Responsive | Invoice Details at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/<id> 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-026 | Layout, Responsive & Usability | Responsive | Outstanding at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/outstanding 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-027 | Layout, Responsive & Usability | Responsive | Outstanding at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/outstanding 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-028 | Layout, Responsive & Usability | Responsive | Outstanding at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/outstanding 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-029 | Layout, Responsive & Usability | Responsive | Outstanding at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/outstanding 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-030 | Layout, Responsive & Usability | Responsive | Payment Tracking at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/invoices/tracking 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-031 | Layout, Responsive & Usability | Responsive | Payment Tracking at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/invoices/tracking 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-032 | Layout, Responsive & Usability | Responsive | Payment Tracking at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/invoices/tracking 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-033 | Layout, Responsive & Usability | Responsive | Payment Tracking at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/invoices/tracking 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-034 | Layout, Responsive & Usability | Responsive | Payment List at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/payments/list 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-035 | Layout, Responsive & Usability | Responsive | Payment List at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/payments/list 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-036 | Layout, Responsive & Usability | Responsive | Payment List at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/payments/list 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-037 | Layout, Responsive & Usability | Responsive | Payment List at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/payments/list 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-038 | Layout, Responsive & Usability | Responsive | Record Payment (TDS customer, invoice ticked) at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/payments/record 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-039 | Layout, Responsive & Usability | Responsive | Record Payment (TDS customer, invoice ticked) at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/payments/record 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-040 | Layout, Responsive & Usability | Responsive | Record Payment (TDS customer, invoice ticked) at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/payments/record 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-041 | Layout, Responsive & Usability | Responsive | Record Payment (TDS customer, invoice ticked) at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/payments/record 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-042 | Layout, Responsive & Usability | Responsive | Customer Outstanding at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/payments/customer-outstanding 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-043 | Layout, Responsive & Usability | Responsive | Customer Outstanding at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/payments/customer-outstanding 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-044 | Layout, Responsive & Usability | Responsive | Customer Outstanding at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/payments/customer-outstanding 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-045 | Layout, Responsive & Usability | Responsive | Customer Outstanding at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/payments/customer-outstanding 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-046 | Layout, Responsive & Usability | Responsive | Tasks & Reminders at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/tasks 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-047 | Layout, Responsive & Usability | Responsive | Tasks & Reminders at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/tasks 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-048 | Layout, Responsive & Usability | Responsive | Tasks & Reminders at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/tasks 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-049 | Layout, Responsive & Usability | Responsive | Tasks & Reminders at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/tasks 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-050 | Layout, Responsive & Usability | Responsive | TDS at phone 390 x 700 | Responsive | P1 | Window 390px wide | 1. Open /accountant/settings 2. Scroll the whole page 3. Open any dialog or menu | 390px | No sideways page scroll; tables become cards with labels; buttons reachable; Submit / Save visible without scrolling under the taskbar | Code |  | Not Run
UIX-051 | Layout, Responsive & Usability | Responsive | TDS at tablet 768 x 1024 | Responsive | P2 | Window 768px wide | 1. Open /accountant/settings 2. Scroll the whole page 3. Open any dialog or menu | 768px | No sideways page scroll; wide tables scroll inside their own box; menu becomes a Menu button | Code |  | Not Run
UIX-052 | Layout, Responsive & Usability | Responsive | TDS at laptop 1366 x 768 | Responsive | P2 | Window 1366px wide | 1. Open /accountant/settings 2. Scroll the whole page 3. Open any dialog or menu | 1366px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-053 | Layout, Responsive & Usability | Responsive | TDS at large screen 1920 x 1080 | Responsive | P2 | Window 1920px wide | 1. Open /accountant/settings 2. Scroll the whole page 3. Open any dialog or menu | 1920px | Full layout; no overlapping or cut-off text | Code |  | Not Run
UIX-054 | Layout, Responsive & Usability | Responsive | Sidebar and header at every width | Responsive | P2 | - | 1. Resize from 1920 to 360 | - | Sidebar above 768 px; below it a Menu button opens the same menu | Code |  | Not Run
UIX-055 | Layout, Responsive & Usability | Responsive | On-screen keyboard on a phone | Responsive | P3 | Phone | 1. Tap the Cash Received box | - | Field scrolls into view; Save Payment reachable | Standard |  | Not Run
UIX-056 | Layout, Responsive & Usability | Responsive | Window taller than the visible screen (taskbar) | Responsive | P2 | Window partly under the Windows taskbar | 1. Open Review & Validate | - | Submit is in the header, so it is never hidden | Code |  | Not Run
UIX-057 | Layout, Responsive & Usability | Usability | Keyboard use | Usability | P3 | - | 1. Use Tab, Enter and Esc on the main forms | - | All controls reachable; dialogs close with Esc | Standard |  | Not Run
UIX-058 | Layout, Responsive & Usability | Usability | Colour is not the only signal | Usability | P4 | - | 1. View status badges in greyscale | - | Text labels show the status as well as colour | Standard |  | Not Run
UIX-059 | Layout, Responsive & Usability | Browsers | Main flow in Chrome, Edge, Firefox and Safari | Compatibility | P2 | - | 1. Upload, Review, Submit, Record Payment in each browser | - | Same result; date boxes and pop-up work | Standard |  | Not Run
SEC-001 | Security | Injection | SQL injection in every search box | Security | P1 | - | 1. Type ' OR 1=1 -- into each search and filter box | - | No error, no extra rows | Standard |  | Not Run
SEC-002 | Security | XSS | Script text in remarks and names | Security | P1 | - | 1. Upload a row whose Remarks is <script>alert(1)</script> 2. Open the invoice | - | Shown as plain text; no script runs | Standard |  | Not Run
SEC-003 | Security | IDOR | Invoices and payments of another branch by id | Security | P1 | - | 1. Open /accountant/invoices/<other-branch id> | - | Not found | Code |  | Not Run
SEC-004 | Security | Token | Tampered token | Security | P1 | - | 1. Change the role inside the token | - | 401 and back to login | Standard |  | Not Run
SEC-005 | Security | Upload | Malicious file names or types | Security | P2 | - | 1. Upload .exe, .html, .svg or a file named ../../x.xlsx | - | Only .xlsx or .csv accepted; name is not used as a path | Code |  | Not Run
SEC-006 | Security | CSV | Formula injection in exported CSV | Security | P2 | A remark starting with = | 1. Export and open in Excel | - | Cells starting with = + - @ are prefixed so they don't run (error-rows CSV) | Code |  | Not Run
SEC-007 | Security | API | Cancel and payment endpoints need permission | Security | P2 | - | 1. Call them with a technician token | - | 403 'Forbidden: insufficient permissions' | Code |  | Not Run
SEC-008 | Security | Passwords | Never returned by the API | Security | P1 | - | 1. Inspect /api/auth/me | - | No password or hash | Standard |  | Not Run
DBC-001 | Database Checks (phpMyAdmin / SQL) | Upload | After Upload & Validate | Integration | P1 | - | 1. Open invoice_imports and invoice_import_rows | ALL_CASES_invoice_upload_TDS2pct.xlsx | 1 import row (PREVIEWED); 42 import rows with matched_customer_id and matched_site_id filled for valid rows | Code |  | Not Run
DBC-002 | Database Checks (phpMyAdmin / SQL) | Submit | After Submit | Integration | P1 | - | 1. Open invoices, invoice_tds, invoice_import_rows, invoice_imports | ALL_CASES_invoice_upload_TDS2pct.xlsx | invoices +41, invoice_tds +41, import rows have created_invoice_id, import is CONFIRMED | Code |  | Not Run
DBC-003 | Database Checks (phpMyAdmin / SQL) | Submit | Join query shows everything connected | Integration | P1 | - | 1. Run: SELECT i.invoice_number, c.name, s.name, b.name, i.status, t.tds_rate, t.expected_tds FROM invoices i JOIN companies c ON c.id=i.customer_id LEFT JOIN sites s ON s.id=i.site_id LEFT JOIN branches b ON b.id=s.branch_id LEFT JOIN invoice_tds t ON t.invoice_id=i.id | - | Every row has a customer, site, branch and TDS row | Code |  | Not Run
DBC-004 | Database Checks (phpMyAdmin / SQL) | Ids | Ids are UUIDs | Functional | P4 | - | 1. Look at companies.id, sites.id, invoices.id | - | 36-character UUIDs (not auto-increment numbers) | Code |  | Not Run
DBC-005 | Database Checks (phpMyAdmin / SQL) | Status | Stored status equals the screen | Integration | P1 | - | 1. Compare invoices.status with Invoice List | - | Identical for every invoice | Code |  | Not Run
DBC-006 | Database Checks (phpMyAdmin / SQL) | Status | Late invoices are OVERDUE in the table | Integration | P1 | - | 1. SELECT status FROM invoices WHERE due_date < CURDATE() AND status NOT IN ('PAID','CANCELLED') | - | Only OVERDUE (no PENDING or PARTIAL) | Code |  | Not Run
DBC-007 | Database Checks (phpMyAdmin / SQL) | Payment | After a payment with TDS | Integration | P1 | - | 1. Open payments, payment_allocations, tds_transactions, invoices, invoice_tds | - | paid_amount and pending_amount updated; deducted_tds and pending_tds updated; tds_type CURRENT or PREVIOUS | Code |  | Not Run
DBC-008 | Database Checks (phpMyAdmin / SQL) | Delete | Deleting an upload from Recent Uploads | Integration | P2 | - | 1. Remove an upload 2. Check the tables | - | invoice_imports row deleted and its rows cascade; invoices, invoice_tds and payments untouched | Code |  | Not Run
DBC-009 | Database Checks (phpMyAdmin / SQL) | TDS | Customer TDS fields | Integration | P2 | - | 1. Open companies | - | tds_applicable 1 and tds_rate 2.00 for TDS customers, 0 and NULL otherwise | Code |  | Not Run
DBC-010 | Database Checks (phpMyAdmin / SQL) | Counts | Amounts add up | Integration | P2 | - | 1. SUM(invoice_amount), SUM(paid_amount), SUM(pending_amount) for non-cancelled invoices | - | paid + pending = amount for every invoice; equals the dashboard and Payment Tracking numbers | Code |  | Not Run
DBC-011 | Database Checks (phpMyAdmin / SQL) | Data | Test data cleanup | Functional | P4 | - | 1. Run cleanup_all_test_customers_and_sites.sql | - | Removes only test customers and sites that have no invoices | Code |  | Not Run
E2E-001 | End-to-End Scenarios | Month flow | Upload, review, submit, pay, report | Integration | P1 | TDS set for customers | 1. Upload ALL_CASES_invoice_upload_TDS2pct.xlsx 2. Check the pop-up and Review 3. Submit 4. Check Invoice List and Outstanding 5. Record the payments in the ALL_CASES workbook (P01 to P19) 6. Check Payment List, Invoice Details, Dashboard, Payment Tracking | ALL_CASES_invoice_upload_TDS2pct.xlsx | Final statuses and TDS equal the Test Plan sheet of the ALL_CASES workbook; database equals the screens | Code |  | Not Run
E2E-002 | End-to-End Scenarios | Five statuses | One invoice per status | Integration | P1 | - | 1. Follow the Status Plan sheet of FIVE_STATUS_invoice_upload.xlsx | FIVE_STATUS_invoice_upload.xlsx | Overdue, Partially Paid, Paid, Cancelled, Pending shown, stored the same | Code |  | Not Run
E2E-003 | End-to-End Scenarios | Validation flow | Mixed file, then fix and re-upload | Integration | P1 | - | 1. Upload VALIDATION_all_cases_invoice_upload.xlsx 2. Download Error Rows 3. Fix and upload again | VALIDATION_all_cases_invoice_upload.xlsx | Errors explained, valid rows saved once, no duplicates on the second upload | Code |  | Not Run
E2E-004 | End-to-End Scenarios | TDS flow | Miss the TDS, add it later | Integration | P1 | TDS customer | 1. Pay an invoice in full with TDS 0 2. Next payment: Add Previous TDS for it | - | Invoice stays PAID; TDS PENDING then CLEARED; history shows Current and Previous | Code |  | Not Run
E2E-005 | End-to-End Scenarios | Late flow | Overdue invoice paid in two parts | Integration | P1 | OVERDUE invoice | 1. Pay part 2. Pay the rest | - | OVERDUE after the first payment; PAID after the second | Code |  | Not Run
E2E-006 | End-to-End Scenarios | Dashboard flow | Numbers move after each step | Integration | P2 | - | 1. Note the dashboard 2. Submit 3. Pay 4. Compare each time | - | Tiles and chart change exactly as expected after each step | Code |  | Not Run

## Test Data
A. Upload files (folder docs/test-data/upload-pack/)
File | What it is for | Expected on the Review screen | Notes
ALL_CASES_invoice_upload_TDS2pct.xlsx | 42 invoices covering every status, TDS (2%) and non-TDS customers, due-date edges. Extra sheets: Test Plan, Payments to Record, Payment Lines. | 42 total, 42 valid, 0 errors | Upload and Submit first. Do not upload twice (all rows would be duplicates).
VALIDATION_all_cases_invoice_upload.xlsx | Every validation rule, row by row. Second sheet 'Expected Results' lists the expected message for each row. | 70 rows counted: 31 valid, 39 errors (one blank row is skipped) | Submit ALL_CASES first (one row repeats an invoice number from it).
EDGE_rows_to_observe.xlsx | 5 rows that pass review but may behave oddly when saved (0.001 amount, 1001-character remark, far future dates). | 5 total, 5 valid | Do not include in a normal run.
FIVE_STATUS_invoice_upload.xlsx | 5 invoices, one for each status. Second sheet 'Status Plan'. | 5 total, 5 valid | Pay …/05889 5,000 and …/1233 10,499; cancel …/3456.
file_level_checks/01_missing_columns.xlsx | No Site and Amount column | 'The file is missing these columns: Site, Amount. Please use the template.'
file_level_checks/02_headers_only.xlsx | Only the header row | 'The file has no invoice rows.'
file_level_checks/03_corrupt_file.xlsx | Text renamed to .xlsx | 'The file could not be read. Please upload a valid .xlsx or .csv file.'
file_level_checks/04_wrong_type.pdf, 05_wrong_type.png | Wrong file types | Rejected: only .xlsx or .csv
file_level_checks/06_over_5MB.xlsx | 5.6 MB | 'The file is too large (maximum 5 MB)'
file_level_checks/07_5000_rows.xlsx | Exactly 5000 rows | 5000 total, 5000 valid | Also a speed test; do not Submit unless you want 5000 invoices.
file_level_checks/08_5001_rows.xlsx | One row over the limit | 'The file has more than 5000 rows. Please split it into smaller files.'
file_level_checks/09_alternate_headers.xlsx | Other header spellings, shuffled columns | 8 total, 8 valid
B. Test customers in the database (codes)
Customer (code) | TDS | Branch / status | Sites
Bluewave Hotels Pvt Ltd (BWH01) | 2% | Head Office | Bluewave - Indiranagar, - Whitefield, - Koramangala, - Old Warehouse (inactive)
Sunrise Apartments Owners Assn (SAO02) | none | Head Office | Sunrise - Tower A, - Tower B, - Clubhouse
Kaveri Tech Park LLP (KTP03) | 2% | Head Office | Kaveri - Block 1, - Block 2, - Food Court
Green Meadow School (GMS04) | 2% | Head Office | Green Meadow - Main Campus, - Annex
Lotus Diagnostics Centre (LDC05) | 2% | Head Office | Lotus - Jayanagar Lab, - HSR Lab
Café Zoë & Sons (Pvt) Ltd (CZS06) | none | Head Office | Café Zoë - Main Outlet, - Kiosk 2
Twin Traders (TWN07A and TWN07B - same name) | none | Head Office | Twin Traders - Shop 1 / Shop 2
Dormant Stores Ltd (DRM09) | none | INACTIVE customer | Dormant - Store
Southern Foods Co (SFC10) | none | other branch (abc) | Southern - Depot
Orchid Bakers & Confectioners (OBC11) | none | Head Office | Orchid - Central Bakery, - Mall Outlet
Silverline Logistics Pvt Ltd (SLL12) | 2% | Head Office | Silverline - Hub 1, - Hub 2
D'Souza & Daughters Jewellers (DSD13) | 2% | Head Office | D'Souza - Commercial Street
ಶ್ರೀ ಲಕ್ಷ್ಮಿ ಸ್ಟೋರ್ಸ್ (SLS14) | none | Head Office | ಶ್ರೀ ಲಕ್ಷ್ಮಿ - ಮುಖ್ಯ ಅಂಗಡಿ
24x7 Fitness Studios (FIT15) | 2% | Head Office | 24x7 - Koramangala Studio
Maple Leaf International School (MLS16) | 2% | Head Office | Maple Leaf - Junior Wing, - Senior Wing
Harbor View Resorts (HVR17) | 2% | Head Office | Harbor - Beach Block
Customer with a 195-character name (LNG18) | none | Head Office | Extra Long Name - Plant
Quick Fix Plumbing (QFP19) | none | Head Office | Quick Fix - Shop 5, Ground Floor
Ambar Textiles (ABT20) | 2% | Head Office | Ambar - Godown A, - Godown B (closed, inactive site)
Northstar Clinics (NSC21) | 2% | Head Office | Northstar - Clinic 1, - Clinic 2
Brightside Coaching Institute (BCI22) | none | other branch (abc) | Brightside - Annex (other branch)
Narayana Hrudayalaya, OSB India Pvt Ltd, The Big Market, Cadabams Diagnostics LLP | Narayana 2%, others none | Head Office | Electronic City, Telegana, chandapura, jayanagar, kanakapura (used by the FIVE_STATUS file)
C. Invoice status rules
Status | Condition | Set when | Shown as
PENDING | Nothing settled, due date not passed (or no due date) | Invoice is saved by Submit | Pending
PARTIAL | Part settled, due date not passed | A payment covers part of the invoice | Partially Paid
OVERDUE | Not fully paid and the due date has passed | Backend sync: at start-up, daily 00:05, and after upload Submit, payment, create or edit | Overdue
PAID | Cash + TDS settled equals the invoice amount (pending 0) | A payment settles the rest | Paid
CANCELLED | Cancelled while nothing had been paid | Cancel action (no button in the accountant panel) | Cancelled
D. TDS status rules (customer with 2% TDS)
TDS status | Condition | Example (₹50,000 invoice)
NOT_APPLICABLE | Customer has no TDS when the invoice was saved | -
PENDING | Nothing deducted yet | Expected 1,000, deducted 0
PARTIAL | Some deducted, less than expected | Deducted 500 of 1,000
CLEARED | All expected TDS deducted | Deducted 1,000 of 1,000

## Defect Log
Defect ID | Test ID | Module | Title | Steps to reproduce | Expected | Actual | Severity | Status | Reported by | Date | Assigned to | Fixed in build | Retest result
DEF-001 | PAY-030 | Record Payment | EXAMPLE: cash more than pending is accepted | 1. Open Record Payment 2. Pending 30,000 3. Cash 31,000 4. Save | Blocked with a message | Payment saved | High | Open | Tester | 2026-09-21 | Developer